| Objective | Area of dev | Actions | When | Who | Partners | Achievement Indicators & outcomes | Review |
| --- | --- | --- | --- | --- | --- | --- | --- |
| - Build new clubhouse | New CSA clubhouse required | Participate fully in the clubhouse redevelopment | Q1 2008 | CSA | NSF | - Working clubhouse fit for purpose |  |
| - Secure additional pitches | More pitches are required to cater for the amount of rugby played by youth & minis | The search has begin for land | 2007 | CSA |  | Additional land to train on Additional pitches to play fixtures |  |
| - Secure RFU Seal of Approval for Youth/Mini sections | Collate all the information to produce the SoA assessment file. Produce 12 month plan. | Review & submit the SoA assessment file & action plan | Oct 07 Jun 08 Oct 08 | PT/RG/SW/CD SH/SR | Active Surrey, Elmbridge, RFU | Year 1 SoA award & Clubmark achieved |  |
| - Make the CRFC website the single point of contact for all CRFC activities | Develop the club website to ensure all mini & youth sections are using it fully | All SoA material on website. All managers to use | Q4 2007 | RM/ youth |  | - Set a usage target - Only website used by club |  |
| - Coaching |  |  |  |  |  |  |  |
| - CRFC mini coaching database | Get all information up to date; share drills across agegroups | Regular data review | Q4 2007 | DA |  | Develop role of coaching co-ordinator |  |
| - Hire a Community Rugby Coach | 1. Develop rugby in Elmbridge state schools 2. Develop rugby coaches in the Elmbridge area | 1. Funding secured 2. Hire CRC 3. CRFC determine our 2 target secondary schools | Dec 06 | PT/SH | Esher RFC, Active Surrey, RFU, Vandals RFC, Reeds RFC, Egham RFC | - JWhite in place |  |
| - Improve the level of coaches | Senior club coaches sharing knowledge/drills with mini/youth coaches | Run 3 Coach the coaches nights per year | Nov, Dec, Jan | PT/BD |  | - First event 35 coaches attended |  |
| - Develop more coaches | - Train 15 more Level 1 coaches | Book courses | 2007 |  | RFU | - Number of level 1 coaches |  |
| - Develop more coaches | - Train 30 more TAG coaches | Organise a course at Esher/Cobham | 2006/7 | JW | CRC | - Courses run at both Esher & Cobham |  |
| - Develop more coaches | - Train 5 more Level 2 coaches | Book courses | 2007 | DA? | RFU |  |  |
| - Develop referees | Train more referees | Run a specific referees course at Cobham | Jan |  | London Society | - Elmbridge cluster course run at - Cobham |  |
| - Meet new RFU CRB regulations |  | CRB application form submission | Oct | NM/RG |  | - All coaches, helpers & managers have applied - for CRB | COMPLETE |
| - First Aiders per squad | Train more first aiders per squad; track all first aiders in mini/youth | Organise first aid courses | Q3 2007 | ?? |  | - First aid co-ordinators - Appointed for mini & youth |  |
| - Develop the coaches | Train all mini/youth coaches in SAQ, warmup skills | Run sessions for all coaches at Cobham | Q3 2007 | SR |  | - Fitness co-ordinator - appointed |  |
| - Festivals |  |  |  |  |  |  |  |
| - Run 3 mini festivals |  | Organise | Q3 2007 | GW |  | A2007 2007 A/B/C festivals organised |  |
| - Run 1 youth festival |  | Organise | Q2 2008 | SH |  | Nandos 10s |  |
| - Players & Representation |  |  |  |  |  |  |  |
| - Increase the numbers of players in youth rugby | Ensure 40 mini players transfer to the youth section in Sept | Links between mini & youth | Q3 2007 | SH/TM | RFU, Sportsmatch | - Numbers in youth section |  |
| - Increase county selection of youth players to xx | Recognition for the Cobham county champions | Work with Surrey Rugby | Q3 2007 | SH | Surrey Rugby | - ???? |  |
| - Improve drop off at U15 |  | Sportsmatch | Q3 2007 | SH | RFU, Sportsmatch | - A&B squad at U15 |  |
| - Increase the numbers of players in the youth section | Support A&B squads at all age groups U13 to U18???? | Sportsmatch | Q3 2007 | SH | RFU, Sportsmatch | - A&B squads - from u7 – u18 |  |